Catch-Up Premium Plan

St Stephen’s CE Primary School

December 2020

| Summary information |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| School | St Stephen’s CE Primary School |  |  |  |  |
| Academic Year | 2020-21 | Total Catch-Up Premium | £32,640 | Number of pupils | 443 |

| Guidance |  |
| --- | --- |
| Children and young people across the country have experienced unprecedented disruption to their education as a result of coronavirus (COVID-19). Those from the most vulnerable and disadvantaged backgrounds will be among those hardest hit. The aggregate impact of lost time in education will be substantial, and the scale of our response must match the scale of the challenge. Schools’ allocations will be calculated on a per pupil basis, providing each mainstream school with a total of £80 for each pupil in years reception through to 11. As the catch-up premium has been designed to mitigate the effects of the unique disruption caused by coronavirus (COVID-19), the grant will only be available for the 2020 to 2021 academic year. It will not be added to schools’ baselines in calculating future years’ funding allocations. |  |
| Use of Funds | EEF Recommendations |
| Schools should use this funding for specific activities to support their pupils to catch up for lost teaching over the previous months, in line with the guidance on curriculum expectations for the next academic year. Schools have the flexibility to spend their funding in the best way for their cohort and circumstances. To support schools to make the best use of this funding, the Education Endowment Foundation (EEF) has published a coronavirus (COVID-19) support guide for schools with evidence-based approaches to catch up for all students. Schools should use this document to help them direct their additional funding in the most effective way. | The EEF advises the following: Teaching and whole school strategies - Supporting great teaching - Pupil assessment and feedback - Transition support Targeted approaches - One to one and small group tuition - Intervention programmes - Extended school time Wider strategies - Supporting parent and carers - Access to technology - Summer support |

| Identified impact of lockdown |  |
| --- | --- |
| Maths | Specific content has been missed, leading to gaps in learning and stalled sequencing of journeys. Children still have an appetite for maths and lockdown has not affected their attitudes however they are quite simply, ‘behind’. Recall of basic skills has suffered – children are not able to recall addition facts, times tables and have forgotten once taught calculation strategies. This is reflected in arithmetic assessments. |
| Writing | Children haven’t necessarily missed ‘units’ of learning in the same way as Maths. However they have lost essential practising of writing skills. GAPs specific knowledge has suffered, leading to lack of fluency in writing. Those who have maintained writing throughout lockdown are less affected, however those who evidently didn’t write much have had to work additionally hard on writing stamina and improving their motivation due to the lack of fluency in their ability to write. |
| Reading | Children accessed reading during lockdown more than any other subject. This is something that was more accessible for families and required less teacher input. However, children are less fluent in their reading and the gap between those children that read widely and those children who don’t is now increasingly wide. |
| Non-core | There are now significant gaps in knowledge – whole units of work have not been taught meaning that children are less able to access pre-requisite knowledge when learning something new and they are less likely to make connections between concepts and themes throughout the curriculum. Children have also missed out on the curriculum experiences e.g. trips, visitors and powerful curriculum moments. |

Planned expenditure - The headings below are grouped into the categories outlined in the Education Endowment Foundation’s coronavirus support guide for schools)

| - Teaching and whole-school strategies |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Desired outcome | Chosen approach and anticipated cost | Impact (once reviewed) | Staff lead | Review date? |
| Supporting great teaching: A recovery curriculum will be planned with a focus on pupil mental health, teamwork and cooperation. Purchase resources and plan for year 1 to access a more play based approach to learning in Autumn term 2020 | Additional time for teachers to research and plan non-core subjects. Release time and additional cover will be required to facilitate the additional PPA. (£1000) Purchase additional manipulatives for EYFS/KS1 initially. (£7000) |  | Mary Fillan Elyse Hare | Dec 2021 Jan 2021 |
| Teaching assessment and feedback Teachers have a very clear understanding of what gaps in learning remain and use this to inform assessments of learning that are aligned with standardised norms, giving a greater degree in confidence and accuracy of assessments. | Purchase and implement PASS (pupil attitudes to school and self) Assessments suite. Complete termly tests and analyse outcomes over time, for groups and individuals. Utilise the woodlands inclusion team to administer and analyse the tests. (£3200 and £2800) |  | Mary Fillan | July 21 |
| Transition support Children who are joining school from different settings or who are beginning their schooling with St Stephen’s have an opportunity to become familiar and confident with the setting before they arrive. | A 360 interactive virtual tour of St Stephen’s is arranged and shared with all new starters for both nursery and reception. Additional time is made to cover the teachers to create welcoming videos and also video and personal contact with new starters. (£600) |  | Kelly Wilson | Ongoing |
| Curriculum enrichment For pupils to have an experiential curriculum despite there being no visits or visitors | Purchase Now, Press, Play. This is an immersive audio resource that engages primary school children in the curriculum through emotion, imagination and movement. (£3,100) |  | Helen Loughlin |  |
| Total budgeted cost |  |  |  | £ 17,700 |  |

| - Targeted approaches |  |  |  |  |
| --- | --- | --- | --- | --- |
| Desired outcome | Chosen action/approach | Impact (once reviewed) | Staff lead | Review date? |
| 1-to-1 and small group tuition Identified children will have significantly increased rates of reading fluency and prosody. They will be able to comprehend reading better as a result of being able to read at pace without spending their working memory decoding. They will be confident readers and dips in reading attainment will be negated. | A Reading Fluency Champion will be appointed to support accelerated reader interventions and assessments (£3000) Additional release time and training to support the delivery of accelerated reader (£1000) |  | Helen Loughlin Helen Loughlin | Feb 21 Feb 21 |
| Intervention programme An appropriate reading, writing and maths intervention supports those identified children in reinforcing their understanding of basic maths , reading and writing skills. | An intervention is identified and purchased. Staff within phases are trained and they are able to deliver the intervention confidently (inclusive of entry and exit data). (£1000) |  | Phase leaders | July 21 |
| Extended home learning Identified children are able to access a regular catch-up through internet access The attainment of those identified children improves and effect of lockdown is becoming negated. Pupils will be identified in terms of need and content will be created by staff. | Content will be sent directly to pupils and through our school website for public access. Access will be monitored, and feedback sought. £5000 |  | Jen Halliday | Ongoing |
| Free breakfast club and snack Identified pupils to have access to breakfast club and playtime snacks based on their needs and to address food poverty | Supporting families of vulnerable pupils to enable a positive start to the school day (£300) |  | Mary Fillan | Ongoing |
| Lunchtime sports coach To support children’s social and emotional difficulties, a coach will direct play and improve the quality and quantity of overall physical engagement. | Structured skills and play session and to resolve disputes and ensured high level physical activity. (£30p/h x 5 days a week = 15 weeks Autumn term £2250) |  | Dave Kerr | Ongoing |
| Total budgeted cost |  |  |  | £7,550 |

| 3.Wider Strategies |  |  |  |  |
| --- | --- | --- | --- | --- |
| Desired outcome | Chosen action/approach | Impact (once reviewed) | Staff lead | Review date? |
| Supporting parents and carers Children will have greater opportunities to access learning at home. Home-learning opportunities will not always require parents to engage with the activities, affording the children greater independence and increasing the likelihood that parents can sustain home-learning. Children have access to appropriate stationery and paper-based home-learning if required so that all can access learning irrespective of ability of child/parent to navigate the online learning. | Additional online learning resources will be purchased to support SPAG (SPAG online), reading (Learning by questions) and maths (White Rose maths and mathletics). £5500 2-week home-learning paper packs are purchased and ready to distribute for all children. Stationery packs are to be purchased and set aside for children to take home when home-learning occurs. £4300 |  | Elyse Hare Tim Elcock | Feb 21 Feb 21 |
| Access to technology During the catch-up extended school provision, children can access additional devices so that they can rotate through discrete teaching, reading fluency and independent online activities. | To purchase additional iPads. They are to be used to further support online access to resources for the children accessing extended school time. (£5000) |  | Dean Martin | Feb 21 F |
| Summer Support NA |  |  |  |  |
| Total budgeted cost |  |  |  | £ 40,050 |
|  |  | Cost paid through Covid Catch-Up |  | £32,640 |
|  |  | Cost paid through charitable donations |  | £5,000 |
|  |  | Cost paid through school budget |  | £2,410 |